## Instructions
Gautam Bhetanabhotla		Using the Status tracker

At the end of each week, update the status of all activities completed during the week
The status tracker shown in this worksheet is an example tracker (values filled are during the middle of the week)
Fill in hours spent on each activity during the current week
	If 5 team members each spent an hour, that counts as 5 hours
	Fill in time for activities not fully completed ("ongoing") as well, then update these values during following weeks
During the planning phases, identify the activities to be done during each week
If you spend time on an activity not listed in the tracker, add the activity and list actual hours (need not fill in estimated hours if you didn't estimate it up front)

For new activities, identify the type of activity - documentation, coordination, estimation etc.

At the end of each week, plan ahead for the following week
	Identify people responsible for each activity
	Estimate the hours needed for the activity

PROJECT NUMBER	3
PROJECT NAME	M & E dashboard
PROJECT MENTOR (sponsor)	Suma Niveditha
TEAM MEMBERS	Gautam Bhetanabhotla
	Nikhil Repala
	Anvithraj Reddy Basani
	Pallamreddy Naga Venkata Viswas Reddy
	Saubhanik Chaudhuri

## Status
PROJECT NUMBER	3
PROJECT NAME	M & E dashboard
PROJECT MENTOR (sponsor)	Suma Niveditha

Activity Name	Type	Responsible	Estimated Team Hours	Actual Hours	Status	Comments	Estimation error	Estimation error %
See Instructions sheet for usage
Week 1 (January 13- January 19)
Fix meeting with client	Coordination	Gautam	0.5	0.2	Done		0.3	150
GIT Repository setup	Preparation	Nikhil	1	1	Done		0	0
Client meeting	Coordination	Saubhanik	1	1	Done		0	0

Research existing technology	Preparation	Gautam	2	2.5	Done		-0.5	20
Project synopsis writeup	Documentation	Viswas	2	3	Done		-1	33.33333333

Team Meeting	Coordination	Anvith Raj	1	1.75	Done		-0.75	42.85714286
Status tracker	Documentation	Nikhil	1		Done
Week 2 (January 20 - January 26)
Tailwind setup	Preparation	Gautam	0.5	0.5	Done		0	0
Come up with a sample UI for project page	Design	Gautam	1	1.5	Done		-0.5	33.33333333
Come up with a sample UI for project gallery	Design	Anvith, Viswas	1	1.5	Done		-0.5	33.33333333
Develop questions for requirements elicitation	Documentation	Viswas	3	3.5	Done		-0.5	14.28571429
DataBase Setup	Requirements	Saubhanik	1	1	Done		0	0
Team Meeting	Coordination	Anvith Raj	1.5	1.5	Done		0	0
Status tracker	Documentation	Nikhil	1	0.75	Done		0.25	33.33333333

Week 3 (January 27 - February 2)
Client meeting	Coordination	Gautam	1	1.5	Done		-0.5	33.33333333
Team Meeting	Coordination	Nikhil	2	1.75	Done		0.25	14.28571429
Status tracker	Documentation	Saubhanik	1	0.75	Done		0.25	33.33333333

Project synopsis writeup	Documentation	Viswas	1	1.5	Done		-0.5	33.33333333
Project Plan writeup	Documentation	Anvith Raj	1	1	Done		0	0
Week 4 (February 3 – February 9)
Setup HeroUI	Preparation	Gautam	0.5	0.5	Done		0	0
Mark up project view page (titles only)	Development	Gautam	1	1	Done		0	0
Learn client-side routing	Preparation	Gautam	1	1.5	Done		-0.5	33.33333333
Set up testing framework for frontend	Testing	Gautam	0.25	0.5	Done		-0.25	50
Mark up project view page (titles only)	Development	Gautam	1	1.5	Done		-0.5	33.33333333
Understand log framework	Preparation	Nikhil	1	1	Done		0	0
setup visualizations	Development	Nikhil	2	3	Done		-1	33.33333333
Team Meeting	Coordination	Anvithraj	1	1	Done		0	0
Client meeting	Coordination	Anvithraj	1	1	Done		0	0
UI Design (Figma)	Design	Anvithraj	2	2.5	Done		-0.5	20
Status tracker	Documentation	Nikhil	0.5	0.5	Done		0	0
Week 5 (February 10 – February 16)
SRS documentation	Documentation	Nikhil	3	4	Done		-1	25
Visualization Work	Development	Nikhil	2	2	Done		0	0
Design a timeline view of the project	Design	Gautam	4	4	Done		0	0
Set up testing on the backend	Testing	Gautam	0.5	0.5	Done		0	0
Reorganize testing framework, fix some bugs	Preparation	Gautam	0.1	0.1	Done		0	0

Fix HeroUI bug	Development				Planned
Client meeting	Coordination	Anvith	1	0.75	Done		0.25	33.33333333
						0	0
Week 6 (February 17 – February 23)
Visualization page ( Frontend ) with charts.js	Development	Nikhil	1	1	Done		0	0
Status tracker	Documentation
Design schemas	Design	Saubhanik	2	2	Done		0	0
Project Gallery	Development	Anvith	2	2	Done		0	0
Team Meeting	Coordination	Everyone	2	2	Done		0	0
Implement routing on the frontend	Development	Gautam	2	2	Done

Week 7 (February 24 – March 2)
pie,bar,line charts inclusion in visualization tab	Development	Nikhil	4	4	Done		0	0
Status tracker	Documentation	Gautam, Nikhil	0.5	0.25	Done		0.25	100
Fix HeroUI bug	Development	Gautam	2	4	Done		-2	50
Schema Review	Design	Saubhanik,Viswas	2	2	Done
Team Meeting	Coordination	Everyone			Done		-1	33.33333333
Login page	Development	Viswas	2	3	Done
Client Gallery preliminary design	Development	Anvithraj	1	1	Done

Week 8 (March 3 – March 9)						0.5	33.33333333
Backend for Visualization Tab	Development	Viswas	2	1.5	Done
Client side view of visualization tab	Development	Nikhil	3		Ongoing		0	0
Status tracker	Documentation	Gautam, Nikhil	0.25	0.25	Done		0	0
Team meeting	Coordination	Everyone	2	2	Done		-0.5	33.33333333
Integrate visualizations with backend	Development	Nikhil	2	2	Done		-1	33.33333333
Team meeting	Coordination	Everyone	2	3	Done		0.5	16.66666667
Improve project gallery	Development	Anvith	2	2	Done		1	33.33333333
Fixing backend bugs	Development	Anvith	1	1	Done
Integrate client gallery with backend	Development	Anvith	1	1	Done

Week 9 (March 10 – March 16)						0	0
Team meeting	Coordination	Gautam, Nikhil, Viswas, Saubhanik	2	2	Done
Refactor KPI view to include add KPI button at the top and category-based filtering	Development	Gautam	1		Planned		0.5	16.66666667
Demo of KPI Update from Timeline view	Development	Gautam	3.5	3	Ongoing		1	33.33333333
Implement timeline view	Development	Gautam	4	3	Ongoing		-0.5	33.33333333
Design document	Documentation	Gautam, Nikhil, Viswas	1	1.5	Done		0	0
Update/Edit Visualization frontend integration	Development	Nikhil	2	2	Done		0	0
Providing API endpoint access on gallery frontend	Development	Anvithraj	3	3	Done
Fixing frontend bugs	Development	Anvithraj	1.5	1.5	Done

Week 10 (March 17 – March 23)						-3	75
Refactor KPI view to include add KPI button at the top and category-based filtering	Development	Gautam	1	4	Done		0	0
Demo of KPI Update from Timeline view	Development	Gautam	4	4	Done		-2	33.33333333
Implement timeline view	Development	Gautam	4	6	Done		-1	25
Integrate timeline and KPI view with backend	Development	Gautam	3	4	Done		-2	40
Implement dynamic visualizations linked to KPIs	Development	Nikhil	3	5	Done		-2	66.66666667
Integrate edit KPI with backend	Development	Gautam	1	3	Done		0	0
Update Project Plan	Documentation	Saubhanik	0.25	0.25	Done		0	0
Gallery UI revamp	Development	Anvithraj	3	3	Done		0	0
Obtain previous versions of project documentation	Documentation	Saubhanik	0.25	0.25	Done		-1	16.66666667
Write backend tests	Testing	Viswas	5	6	Done		0	0
Write chart tests	Testing	Nikhil	4	4	Done
Write Project header, timeline and KPI tests	Testing	Gautam	2		Ongoing		0	0
SRS Document updation	Documentation	Nikhil	1	1	Done